## Work Plan Key
Project(s)
Name of Project 1 | Volunteer Intergenerational Art Projects for Holocaust Survivors
Name of Project 2 | Family Caregiver Educational Workshops
Staff Title Key
1) PD = Project Director |  | 2) PE = Project Evaluator
3) PM = Project Manager |  | 4) APM = Assistant Project Manager
5) RA = Research Assistant |  | 6) C = Consultant
7) V = Volunteers |  | 8)

## Project 1 Work Plan
Name of Project 1: Volunteer Intergenerational Art Projects for Holocaust Survivors
Outcome of Project 1: Improved Social Health
Intervention of Project 1: Intergenerational Art Groups
Major Objectives | Lead Person(s) | Time Frame: Periods, Quarters, and Months
|  | Period 1 | [8 empty] | Period 2
|  | (January 1, 2027 - September 30, 2027) | [8 empty] | (October 1, 2027 - June 30, 2028)
Key Tasks |  | P1 Q1 |  |  | P1 Q2 |  |  | P1 Q3 |  |  | P2 Q1 |  |  | P2 Q2 |  |  | P2 Q3
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
|  | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028
1) Key Task: Develop curriculum for intergenerational art programming
Comparative study on successful models of intergenerational art programming | RA | bar: P1 Q1 Jan to P1 Q1 Feb
Compose curriculum and art projects based on favored practices from the comprehensive study | RA, PM | bar: P1 Q1 Mar to P1 Q2 Apr
Get feedback on curriculum from participants | PE | bar: P1 Q2 Apr to P1 Q2 May; P2 Q1 Oct; P2 Q3 Apr
2) Key Task: Select and host art projects for participants
Use best practices from studies to identify possible art projects | RA, PM | bar: P1 Q1 Mar to P1 Q2 May
Finalize art projects and group activities | PM | bar: P1 Q2 Apr to P1 Q2 May
Purchase supplies | PM | bar: P1 Q2 Apr to P1 Q2 May
Host intergenerational art programming | PM | bar: P1 Q2 Jun to P1 Q3 Sep; P2 Q2 Mar to P2 Q3 Jun
3) Key Task: Recruit, train, and assign volunteers
Promote volunteer opportunity | PD, APM
Interview volunteers | PM, APM | bar: P1 Q1 Feb to P1 Q2 Apr; P2 Q1 Oct to P2 Q1 Dec
Provide PCTI training | PM | bar: P1 Q1 Mar to P1 Q2 May; P2 Q1 Oct to P2 Q2 Jan
Assign volunteers to each art class | APM | bar: P1 Q2 Apr to P1 Q2 May; P2 Q1 Dec to P2 Q2 Jan
Volunteers attend programming | APM | bar: P1 Q3 Jul to P1 Q3 Sep; P2 Q2 Mar to P2 Q3 Jun
4) Key Task: Monitor and evaluate curriculum, materials, and mentors
Disseminate JFNA survey for feedback from participants on the curriculum, materials, and program experience | PE, RA | bar: P1 Q3 Sep; P2 Q3 Jun
Conduct interviews with volunteers before and during participation | PE, PM, APM | bar: P1 Q2 Jun; P1 Q3 Aug; P2 Q2 Feb; P2 Q3 May
Adjust program based on participant feedback | PE, RA | bar: P2 Q1 Nov to P2 Q2 Jan
5) Key Task:
Major Objectives | Lead Person(s) | P1 Q1 Jan: Time Frame: Periods, Quarters, and Months
|  | Period 1 | [8 empty] | Period 2
|  | (January 1, 2027 - September 30, 2027) | [8 empty] | (October 1, 2027 - June 30, 2028)
Key Tasks |  | P1 Q1 Jan: P1 Q1; P1 Q2 Apr: P1 Q2; P1 Q3 Jul: P1 Q3; P2 Q1 Oct: P2 Q1; P2 Q2 Jan: P2 Q2; P2 Q3 Apr: P2 Q3
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
|  | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028
6) Key Task:
7) Key Task:
8) Key Task:
9) Key Task:
10) Key Task:

## Project 2 Work Plan
Name of Project 2: Family Caregiver Educational Workshops
Outcome of Project 2: Improved Family Caregiving Experience
Intervention of Project 2: Educational Workshops
Major Objectives | Lead Person(s) | Time Frame: Periods, Quarters, and Months
|  | Period 1 | [8 empty] | Period 2
|  | (January 1, 2027 - September 30, 2027) | [8 empty] | (October 1, 2027 - June 30, 2028)
Key Tasks |  | P1 Q1 |  |  | P1 Q2 |  |  | P1 Q3 |  |  | P2 Q1 |  |  | P2 Q2 |  |  | P2 Q3
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
|  | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028
1) Key Task: Publicize Family Caregiver Workshops
Announce family caregiver workshops across agency and to partners | APM | bar: P1 Q1 Jan to P1 Q1 Mar
Enroll family caregivers in workshops | V, PM | bar: P1 Q2 Jun to P2 Q3 May
2) Key Task: Agency hosts workshops for family caregivers.
Develop workshop curriculum | PD, PM | bar: P1 Q1 Jan to P1 Q2 May
Hire and train session facilitators | PD, PM | bar: P1 Q2 Apr to P1 Q2 Jun
Host workshops | C | bar: P1 Q3 Jul to P1 Q3 Aug; P2 Q1 Oct to P2 Q1 Nov; P2 Q2 Jan to P2 Q2 Feb; P2 Q3 Apr to P2 Q3 May
Follow up group session to solidify lessons learned from consultant | APM | bar: P1 Q3 Sep; P2 Q1 Dec; P2 Q2 Mar; P2 Q3 Jun
Create and provide take home pamphlets for family caregivers in alignment with session topics | RA, APM | bar: P1 Q2 Jun to P1 Q3 Aug; P2 Q1 Oct to P2 Q1 Nov; P2 Q2 Jan to P2 Q2 Feb; P2 Q3 Apr to P2 Q3 May
3) Key Task: Create family caregiver resource hub
Collect and create resources for family caregiver resource hub | PD, PE | bar: P1 Q1 Jan to P1 Q2 May
Add resources to website and build homepage | PD, PM, PE | bar: P1 Q2 May to P1 Q3 Jul
Launch website and share within agency and with partners | C | bar: P1 Q3 Aug to P2 Q3 Jun
4) Key Task: Monitor and Evaluate library engagement, training workshops, and website.
Track numbers of family caregivers participating in the workshops | PE | bar: P1 Q3 Sep to P2 Q3 Jun
Disseminate JFNA survey to measure family caregiver knowledge and feedback on particpation | PE, RA | bar: P1 Q3 Aug; P2 Q1 Nov; P2 Q2 Feb; P2 Q3 May
Track website usage and update/add educational resources in accordance with growth | PE, RA | bar: P1 Q3 Aug to P2 Q3 Jun
5) Key Task:
Major Objectives | Lead Person(s) | P1 Q1 Jan: Time Frame: Periods, Quarters, and Months
|  | Period 1 | [8 empty] | Period 2
|  | (January 1, 2027 - September 30, 2027) | [8 empty] | (October 1, 2027 - June 30, 2028)
Key Tasks |  | P1 Q1 Jan: P1 Q1; P1 Q2 Apr: P1 Q2; P1 Q3 Jul: P1 Q3; P2 Q1 Oct: P2 Q1; P2 Q2 Jan: P2 Q2; P2 Q3 Apr: P2 Q3
|  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
|  | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028
6) Key Task:
7) Key Task:
8) Key Task:
9) Key Task:
10) Key Task: